## Executive Summary
Patch Management Strategy - Executive Summary
Document Version: | 1.0
Effective Date: | February 2026
Document Owner: | Enterprise Architecture / IT Operations
Strategy Overview
This document establishes the enterprise patch management strategy for a three-environment system (DEV, TEST, PROD). It defines the governance framework, operational procedures, risk mitigation controls, and decision criteria required to maintain system security, stability, and compliance while enabling efficient delivery of patches across environments.
Key Assumptions
• DEV, TEST, and PROD environments are logically and physically separated
• Change Management Board (CAB) exists with authority to approve/prohibit changes
• Production changes follow a formal Change Advisory Board (CAB) process
• Automated deployment tooling is available (e.g., CI/CD pipelines)
• Backup and recovery procedures are established for all environments
• The organization has defined SLAs for system availability
Patch Deployment Sequence
Sequence | Environment | Purpose | Typical Lead Time
1 | DEV | Initial validation, development testing | Day 0
2 | TEST / STAGING | Full regression, UAT | Day 1-3
3 | PROD | Production release | Day 5-7

## Patch Promotion Flow
Patch Promotion Flow & Criteria
Entry Criteria per Environment
Environment | Entry Criteria
DEV | Patch package validated by development team; change request created; backup verified
TEST | DEV deployment successful; test cases updated; test data prepared; test environment availability confirmed
PROD | TEST execution results approved; CAB approval obtained; rollback plan documented; communication plan initiated
Exit Criteria per Environment
Environment | Exit Criteria
DEV | Unit tests pass (≥90% coverage); basic integration smoke tests pass; no blocking defects
TEST | All blocking/critical defects resolved; regression test suite pass rate ≥95%; UAT sign-off obtained; performance benchmarks met
PROD | Post-deployment smoke tests pass; monitoring alerts confirmed; business stakeholders notified; documentation updated
Rollback Strategy per Environment
Environment | Rollback Trigger | Rollback Procedure | Max Downtime Tolerance
DEV | Any deployment failure | Redeploy previous baseline from version control | 1 hour
TEST | Critical defects discovered | Restore from TEST backup; redeploy previous version | 4 hours
PROD | Service availability <99.5%; data integrity issues; critical defect affecting >=5% of users | Execute documented backout plan; engage on-call DBA if needed | Per SLA (15-30 min)

## Testing Requirements
Testing & Validation Requirements
Regression Testing Requirements
Scope | Coverage | Ownership | Tooling
Full regression | 100% of functional test cases | QA Team | Automated test framework
Targeted regression | Affected components + downstream dependencies | QA Team + Development | Automated + manual
Ad-hoc / exploratory | Boundary conditions, edge cases | QA Team | Manual
Smoke Testing vs Full Regression Criteria
Factor | Smoke Test | Full Regression
When Used | Every deployment | Weekly or per release
Scope | Critical path (5-10 tests) | Complete suite (200+ tests)
Execution Time | <30 minutes | 4-8 hours
Ownership | Operations + Dev | QA Team
Automation | Fully automated | Automated + manual
Pass Threshold | 100% pass required | ≥95% pass required
UAT Requirements
UAT Sign-off | Required for ALL production deployments
UAT Participants | Business process owners, key end users
UAT Test Cases | Business-critical scenarios only (minimum 15 scenarios)
UAT Duration | Minimum 1 business day for standard patches; 3-5 business days for major releases
UAT Defect Severity | Blocking/critical defects must be resolved before PROD promotion

## Patch Classification
Patch Categorization Framework
Patch Classification Definitions
Classification | Definition | Response SLA | Deployment Target
P1-Critical | Patches addressing active exploits, critical CVEs (CVSS ≥7.0), or confirmed security incidents | 24-48 hours (critical: 4-24 hours) | 4-24 hours
P2-High | Significant security risk, major functionality impact | 4 hours response, 7 days resolution | 5-7 days
P3-Medium | Moderate impact, workaround available | 24 hours response | Monthly cadence
P4-Low | Minimal impact, cosmetic issues, documentation updates | 5 business days | Quarterly
Patch Type Testing Scope
Category | Testing Scope | Approval Level | Rollback Complexity
Infrastructure | Reduced - focus on availability | Standard CAB | High
Database | Moderate - data integrity focus | DBA Lead + CAB | Critical
Middleware | Moderate - integration focus | Standard CAB | Medium
Application | Full - functional + integration | Standard CAB | Low

## Governance Controls
Governance & Controls
Change Management Approvals per Environment
Environment | Approval Required | Approver | Lead Time
DEV | Notification only | Development Lead | Same day
TEST | Change request approval | Test Manager | 24 hours
PROD | CAB approval (standard) | CAB (majority) | 5 business days
PROD | Emergency approval | CAB Chair + Security Lead | 4-24 hours
Communication Plan
Stakeholder | Notification Trigger | Timing | Channel
Development Team | Patch available in DEV | Upon release | Teams / Email
QA Team | Deployment to TEST | 24 hrs before | Teams / Email
Business Stakeholders | PROD deployment planned | 5 business days before | Email
End Users | PROD deployment | 48 hours before (planned) | Portal / Email
CAB | All changes | Per approval timeline | Agenda + Email
IT Operations | All deployments | 24 hours before | Teams / PagerDuty
Security Team | Security patches | Immediate | Teams / Phone
Documentation Requirements
Document | Required For | Retention
Change Request (CR) | All environments | 7 years
Test Results Report | TEST + PROD | 5 years
UAT Sign-off | PROD | 5 years
Rollback Procedure | PROD | 5 years
Post-Implementation Review (PIR) | PROD | 7 years
Security Impact Assessment | Security patches, major upgrades | 7 years

## RACI Matrix
RACI Matrix for Patch Activities
Activity | IT Ops | Development | QA | Security | CAB | Business
Patch source identification | R | C | I | R | I | -
Patch testing in DEV | C | R | C | I | - | -
Change request creation | R | C | C | C | I | I
TEST environment deployment | R | C | C | I | - | -
Regression test execution | C | C | R | I | - | -
UAT coordination | I | C | R | I | I | R
CAB approval | I | C | C | C | R | I
PROD deployment execution | R | C | I | C | I | -
Post-deployment validation | R | C | C | C | - | -
Post-implementation review | R | C | C | C | C | I
Rollback execution | R | C | - | C | I | -
Legend: R=Responsible, A=Accountable, C=Consulted, I=Informed

## Templates & Checklists
Templates & Checklists
Entry/Exit Criteria Checklist
Phase | Checklist Item | Status
Pre-DEV | Change request created and assigned
Pre-DEV | Patch package validated by development team
Pre-DEV | Backup verified and documented
Pre-TEST | DEV deployment successful
Pre-TEST | Test cases updated for new functionality
Pre-TEST | Regression test suite ready
Pre-PROD | TEST execution results approved
Pre-PROD | Regression test pass rate ≥95%
Pre-PROD | UAT sign-off obtained
Pre-PROD | CAB approval obtained
Pre-PROD | Rollback plan documented and tested
Post-PROD | Post-deployment smoke tests pass
Post-PROD | Monitoring alerts confirmed operational
Post-PROD | Database integrity confirmed
Post-PROD | Business stakeholders notified

## SOP - Overview
SOP - Playbook Overview
Purpose and Scope
This operational playbook provides step-by-step procedures for executing patch deployments across the three-environment system (DEV → TEST → PROD). It translates the Patch Management Strategy into actionable tasks for operations teams.
Target Audience
Role | Use This Playbook For
IT Operations Engineers | Executing deployments, validations, rollbacks
DevOps Engineers | Pipeline execution, automation troubleshooting
Help Desk/Support Staff | Understanding deployment status, user communication
Test Engineers | TEST environment deployment and validation
On-Call Engineers | Emergency response, incident handling
When to Use This Playbook
Use this playbook when: • Deploying routine monthly patches • Applying security patches (planned or emergency) • Executing major version upgrades • Performing emergency patch response • Executing rollback procedures • Validating post-deployment system state

## SOP - Deployment Steps
SOP - Deployment Procedures
DEV Deployment Steps
1. Prepare the deployment environment
2. Stop dependent services
3. Execute pre-deployment backup
4. Apply the patch
5. Start services
6. Execute smoke tests
7. Verify basic functionality
8. Document deployment results
TEST Deployment Steps
1. Verify DEV success before promoting to TEST
2. Prepare the TEST deployment environment
3. Stop TEST environment services
4. Execute pre-deployment backup
5. Apply the patch
6. Start services and verify
7. Execute smoke tests (100% pass required)
8. Execute regression test suite
9. Notify QA team for manual testing
10. Obtain UAT sign-off
PROD Deployment Steps
1. Final pre-deployment verification
2. Send deployment start notification
3. Enter maintenance window
4. Stop production services
5. Execute production backup
6. Apply the patch
7. Verify patch application
8. Start production services
9. Execute post-deployment smoke tests
10. Verify monitoring and alerting
11. Execute data integrity checks
12. Send deployment completion notification

## SOP - Rollback
SOP - Rollback Procedures
Decision Triggers (When to Rollback)
Trigger | Threshold | Action
Service Availability | <99.5% | Immediate rollback
Critical Defects | ≥5% users affected | Immediate rollback
Data Integrity | Any confirmed issue | Immediate rollback
Security Vulnerability | CVSS ≥7.0 discovered | Fast-track rollback
Smoke Test Failure | Any failure in PROD | Evaluate + decide
Performance Degradation | >20% slower | Evaluate impact
Rollback Decision Authority
DEV | Lead Developer
TEST | Test Manager + Development Lead (joint)
PROD | CAB Chair + IT Operations Manager (joint)
Rollback Procedure Summary
1. Confirm rollback decision - Obtain required approvals (CAB Chair + IT Ops Manager)
2. Send rollback notification
3. Enter maintenance mode
4. Stop production services
5. Restore production backup
6. Start production services
7. Verify rollback success
8. Send rollback completion notification

## SOP - Troubleshooting
SOP - Troubleshooting Guide
Patch Deployment Failures
Issue: Deployment script fails
1. Check error message in output
2. Review deployment logs: tail -100 /var/log/[deployment].log
3. Verify file permissions: ls -la /opt/[application]
4. Verify disk space: df -h
5. Check dependencies: ldd /opt/[application]/bin/[binary]
6. Retry deployment if transient error
Issue: Service won't start after patch
1. Check service status: systemctl status [service]
2. Review startup logs: journalctl -u [service] -n 100
3. Verify configuration syntax: nginx -t
4. Check port conflicts: ss -tuln ¦ grep [port]
5. Verify file permissions
6. Check dependencies: ldd on libraries
7. Rollback if unresolvable
Performance Degradation
Issue: Application slow after patch
1. Check resource utilization: top, free -h, iostat
2. Compare with baseline metrics
3. Check database query performance
4. Verify index usage
5. Check for new bottlenecks
6. Enable slow query logging if database
7. Rollback if >20% degradation
Data Integrity Concerns
Issue: Data inconsistency after patch
1. HALT deployment immediately
2. Do NOT make any changes
3. Verify data with pre-deployment backup
4. Compare record counts
5. Check referential integrity
6. Execute ROLLBACK immediately
7. Escalate to DBA Lead

## SOP - Emergency
SOP - Emergency Patch Procedures
Trigger Criteria for Emergency Classification
Criterion | Threshold | Example
Active Exploitation | Confirmed in-the-wild exploit | CVE with public PoC
CVSS Score | ≥9.0 (Critical) | Remote code execution
Service Availability | Immediate risk | Ransomware indicators
Regulatory Directive | Required immediate action | Compliance enforcement
Business Impact | Complete system outage potential | Critical system down
Accelerated Approval Process
1. Contact emergency approvers in parallel: CAB Chair, Security Lead, IT Operations Manager
2. Provide emergency approval request with CVSS score and risk assessment
3. Obtain verbal approval (document in CR) - document approver name, time, conditions
4. Document expedited approval in CR - Approval type, Approvers, Approval time, Conditions
Compressed Deployment Timeline
Phase | Standard | Emergency
Approval | 5 days | 4-24 hours
DEV Deployment | 1 day | Same day
PROD Deployment | 1-2 days | 4-12 hours
Post-Deploy Validation | Standard | 24-48 hours in TEST
Post-Incident Review Requirements
1. Schedule Post-Incident Review (PIR) within 5 business days of deployment
2. Document PIR agenda: Timeline, Effectiveness, Process improvements, Lessons learned
3. Complete PIR documentation: Root cause, Response effectiveness, Deviations, Recommendations
4. Submit PIR to CAB for review and archive for compliance